## QualityStatusRep.-Vend.Packages
TENTATIVE
[15 empty] | QUALITY STATUS REPORT | [17 empty] | CONFIRMED
OVERDUE
Req # | Vendor | Abbreviation | Country | Req Title / CTR No | Engineer [WP] | Buyer [WP] | Expediting [WP] | PWHT / NDE-NDT [WP] | QAQC [WP/TANAP] | Engineer [TNP] | Buyer [TNP] | TPI | Discipline | RFQ # | Latest Status | Critically Inspection Regime | Manufacturing. Time (week) | Shop Inspection per week (days) | Schedule Plan | Bids Received Client | Bids Received EPCM | PO Issued | Key Vendor Docs Approval | Kick Off Meeting (KOM) | KOM MOM Number | PQP Status | ITP Status | J Type Document Status (WPS+NDT+Etc.) | Pre Inspection Meeting (PIM) | Production Start Date | PIM MOM Number | FAT Date | MRB Sub. Date | Material Release Date | First Delivery Date to Site | Final Delivery to Site [Completion] | Required on Site Phase 0
MECHANICAL |  |  |  |  | EPCM |  |  |  |  | TANAP
WRP-REQ-MEC-CSG-016 | GE | GEO | ITALY USA | Main Line Compression Trains TUCO (LLI) [inc. temporary strainers] TPI-11 |  |  |  |  | AFSHIN MAAF KAAN DONMEZ | NERIMAN MEHDIYEV | PINAR COSKUN | 1-ALESANDRO BONALDI 2-MASSIMO PETRACCHI 3-DINO DENTINI 4-DAVIDE MATTEONI TEMP: VICENZO CAP. | ME | ILF-RFQ-PCP-GEN-004A | Hazop / SIL review held at EPCM offices. | A/1 | 97 | 7 | Planned Date: | 07-Oct-14 |  | 2015-07-01 | 2015-09-23 | 28-Jul-14 | TANAP-WRP-MOM-GEO-0001 | 2015-11-09 | 2015-11-09 | 2015-11-11 | 20-Oct-14 | 2015-10-20 | TANAP-WRP-MOM-GEO-0002 | 2016-07-25 |  | 2016-09-09 | 2017-01-16 | 2017-03-24 | 2017-04-30
[19 empty] | Actual Date: | 2015-04-20 | 2015-04-20 |  |  |  |  | Rev:P3-1 | Rev:RP3-1 | J Type Issued 19 / 21 - 90 % |  |  |  | 2016-09-09 |  | 2016-09-19 |  |  | 2017-06-30
WRP-REQ-MEC-CS5-002 | SOLAR TURBINES | SOL | USA BELGIUM | Offtake-Booster Compression Trains TUCO TPI-12 |  |  |  |  | AFSHIN MAAF KAAN DONMEZ | N MEHDIYEV | PINAR COSKUN | 1-TOM BROWN 2-BOB RASOOLI TEMP: SID HODKINS | ME | ILF-RFQ-PCP-GEN-004B | Hazop / SIL review held at EPCM offices. | A/1 | 75 | 7 | Planned Date: |  |  | 2015-09-15 | 2015-10-16 | 2015-09-02 | TANAP-WRP-MOM-SOL-0001 | 2015-10-23 | 2015-11-06 | 2015-11-20 | 01-Dec-14 | 2015-10-20 | TANAP-WRP-MOM-SOL-0004 | 2016-07-19 |  | 2016-08-03 | 2016-12-29 | 2016-12-29 | 2016-09-01
[19 empty] | Actual Date: | [6 empty] | Rev:P3-0 | Rev:P3-2 | J Type Issued 8 / 8-100%
WRP-REQ-MEC-GEN-006 | CDB ENGINEERING | CDB | ITALY | LP Fuel Gas Heaters (Electric Type) TPI-13 |  |  |  |  | D LAWRIE AFSHIN MAAF | N MEHDIYEV | PINAR COSKUN | 1-ENZO TREMOLADA 2- EMILIANO LUNGO | ME | WRP-RFQ-PCP-GEN-003 | Critical ( re-submission) - 11st Submission ( non -critical) - 23 overdue Re-submission ( non-critical) - 14 Some J-Type document overdue ! | B/2 |  | 0.5 | Planned Date: | 10-Feb-15 |  | 2015-11-16 |  | 03-Dec-14 | TANAP-WRP-MOM-CDB-0001 | 2016-02-11 | 2016-02-22 | 2016-02-11 | 2016-04-19 | 2016-04-25 | TANAP-WRP-MOM-CDB-0002 |  |  |  | 2016-12-15 | 2017-12-15 | 2016-10-01
[17 empty] | 75 |  | Actual Date: | 2015-05-18 | 2015-05-27 |  |  |  |  | Rev:P3-0 | Rev:P3-1 | J Type Issued 5 / 13 -40%
WRP-REQ-MEC-GEN-018 | CDB ENGINEERING | CDB | ITALY | HP Fuel Gas Heater (Water Bath type) + Process Heaters TPI-13 |  |  |  | Note 1 | DOUGLAS LAWRIE AFSHIN MAAF | N MEHDIYEV | PINAR COSKUN | 1-ENZO TREMOLADA 2- EMILIANO LUNGO 3- UBERTI FOPPA | ME | WRP-RFQ-PCP-GEN-011 | Critical ( re-submission) - 11st Submission ( non -critical) - 23 overdue Re-submission ( non-critical) - 14 Some J-Type document overdue ! | B/2 |  | 0.5 | Planned Date: | 10-Feb-15 |  | 2015-11-16 | 2016-01-11 | 04-Dec-14 | TANAP-WRP-MOM-CDB-0001 | 2016-02-11 | 2016-02-16 | 2016-02-11 | 2016-04-19 | 2016-04-26 | TANAP-WRP-MOM-CDB-0002 |  |  |  | 2016-12-15 | 2017-11-15 | 2016-11-01
[17 empty] | 75 |  | Actual Date: | 2015-05-18 | 2015-05-27 |  |  |  |  | Rev:P3-0 | Rev:P3-0 | J Type Issued 5 / 13 -40%
WRP-REQ-MEC-GEN-007 | TBC | TBA |  | Centrifugal Pumps (API and Non-API) TPI-14 |  |  |  | Note 1 | DOUGLAS LAWRIE AFSHIN MAAF | N MEHDIYEV | ELNUR MAMMADOV | TBA | ME | WRP-RFQ-PCP-GEN-004 | TANAP evaluating preservation procedure prior to award. PO Award imminent.Proposed Kick Off Meeting to be determined subject to formal Award of Contract | C/3 |  | 0.25 | Planned Date: | 10-Feb-15 |  | 2016-06-18 | 12-May-15 | 2016-07-15 |  | 2016-08-15 | 2016-08-15 | 2016-08-30 | 2016-08-20 | [5 empty] | 2016-10-14 | 2017-05-01 | 2017-01-01
[17 empty] | 75 |  | Actual Date: | 2015-07-13 | 2015-07-23 |  | 2016-01-26
WRP-REQ-MEC-GEN-009 | ATLAS COPCO | ATL | UK | Air Compressors (Plant Air Systems) TPI-15 |  |  |  | Note 1 | KIVANÇ AĞİÇ EMRE EVGI | N MEHDIYEV | ELNUR MAMMADOV | 1-DONOVAN DENNIS 2- ? FIORE: ALESANDRO MATTARA | ME | WRP-RFQ-PCP-GEN-005 | Some J-Type document overdue ! PQP Shall be revised and issued ! | B/2 |  | 2 | Planned Date: | 03-Feb-15 |  | 2015-11-19 | 2015-12-31 | 30-Nov-14 | TANAP-WRP-MOM-ATL-0001 | 2016-01-15 | 2016-01-12 | 2016-02-20 | 2016-03-08 | 2016-06-10 | TANAP-WRP-MOM-ATL-0003 |  |  |  | 2017-01-15 | 2017-09-30 | 2016-11-01
[17 empty] | 80 |  | Actual Date: | 2015-05-14 | 2015-05-27 |  |  |  |  | Rev:P3-0 | Rev:P3-2 | 26/30 - 82%
WRP-REQ-MEC-GEN-010 | RM GAZ | RMG | TURKEY | Pressure Vessels TPI-16 |  |  |  | Note 1 | KIVANÇ AĞİÇ EMRE EVGI | N MEHDIYEV | PINAR COSKUN | 1- FURKAN KAYA 2- SUAT TUNC | ME | WRP-RFQ-PCP-GEN-006 | Field Expediting visit carried out 07 Mar 2016. Next visit TBA. Some J-Type document overdue ! | C/3 |  |  | Planned Date: |  |  | 2015-11-06 | 2015-12-18 | 25-Nov-15 | TANAP-WRP-MOM-TNP-0955 | 2016-02-17 | 2016-02-15 | 2015-12-19 | 2016-04-05 | 2016-07-14 | TANAP-WRP-MOM-RMG-0002 |  |  |  | 2016-12-31 | 2017-12-31 | 2017-01-01
[17 empty] | 75 | 0.5 | Actual Date: | 2015-08-11 | 2015-08-14 |  |  |  |  | Rev:RP3-2 | Rev:RP3-4 | 4/ 6 - %60
WRP-REQ-MEC-GEN-014 | INTERGEN SRL. | IML | ITALY | Diesel Engine Generators TPI-17 |  |  |  | Note 1 | DOUGLAS LAWRIE HUSAMETTIN PEHLIVAN | N MEHDIYEV | A HASTURK | 1- GIORGIO PARENTI 2- STEFANO LECCHI | ME | WRP-RFQ-PCP-GEN-008 | First IML action tracker meeting held, deliverables coming in as per VDS | B/2 | 75 | 0.5 | Planned Date: | 16-Feb-15 |  | 2016-02-08 | 09-May-15 | 2016-03-03 | TANAP-WRP-MOM-IML-0001 | 2016-03-15 | 2016-03-15 | 2016-05-25 | 2016-05-10 | 2016-06-06 | TANAP-WRP-MOM-IML-0002 |  |  |  | 2017-01-16 | 2017-05-01 | 2017-02-01
[19 empty] | Actual Date: | 2015-08-03 | 2015-09-22 |  |  |  |  | Rev:RP3-0 | Rev:P3-0 | 1/10 - 10%
WRP-REQ-MEC-GEN-015 | ILTEKNO | ILT | TURKEY / GERMANY | Gas Engine Generators TPI-18 |  |  |  | Note 1 | DOUGLAS LAWRIE HUSAMETTIN PEHLIVAN | N MEHDIYEV | A HASTURK | 1- PAUL NEUMANN 2-? | ME | WRP-RFQ-PCP-GEN-009 | EPCM returned informal comments on draft A01 VDS and A02 Fabrication Schedule, a/w revised submissions, due 17/18-Mar. | B/2 |  | 0.5 | Planned Date: | 13-Feb-15 |  | 2016-02-01 | 15-May-15 | 2016-02-23 | TANAP-WRP-MOM-ILT-0001 | 2016-04-05 | 2016-04-05 | 2016-06-17 | 2016-07-27 | 2017-06-01 |  |  |  |  | 2016-12-12 | 2017-06-01 | 2017-02-01
[17 empty] | 75 |  | Actual Date: | 2015-08-03 | 2015-08-14 |  |  |  |  | Rev:RP3-C | Rev:RP3-C | 0/11 - 0%
WRP-REQ-MEC-GEN-016 | KTS | KTS | FRANCE QATAR | Air Cooled Heat Exchangers TPI-19 |  |  |  | Note 1 | KIVANÇ AĞİÇ EMRE EVGI | N MEHDIYEV | A HASTURK | 1- FREDRIC CHESNIN (FRANCE) 2- ? 1- THARIK SHAUKATH (QATAR) 2- RAMASAMY VEERAPPAN (QATAR) | ME | WRP-RFQ-PCP-GEN-010 | PO Awarded 24-Nov, Contract received via DCC 27-Nov, Kick-off Meeting held 17th / 18th Dec. Some J-Type document overdue ! | B/2 | 75 | 0.5 | Planned Date: | 28-Jan-15 |  | 2015-11-24 | 2016-01-19 | 17-Dec-14 | TANAP-WRP-MOM-KTS-0001 | 2016-02-26 | 2016-02-16 | 2016-01-29 | 2016-04-19 | 2016-05-15 | TANAP-WRP-MOM-KTS-0002 |  |  |  | 2016-12-31 | 2017-09-30 | 2016-11-01
[19 empty] | Actual Date: | 2015-06-01 | 2015-06-04 |  |  |  |  | Rev:P3-2 | Rev:RP3-0 | 6 / 8 - %75
WRP-REQ-MEC-GEN-002 | VALVITALIA | VPS | ITALY | Filter Separators + Process Filters TPI-21 |  |  |  | Note 1 | KIVANÇ AĞİÇ EMRE EVGI | N MEHDIYEV | PINAR COSKUN | 1-RICHARDO CHEROTTI 2-ALESSANDRO MATTARA | ME | WRP-RFQ-PCP-GEN-002 | Production Schedule Issued 19/02/2016. Action tracker weekly meeting now taking place. Some J-Type document overdue ! | B/2 |  | 0.5 | Planned Date: | 06-Jan-15 |  | 2016-01-20 | 2016-01-05 | 2016-02-03 | TANAP-WRP-TRA-VPF-0001 | 2016-02-29 | 2016-02-15 | 2016-03-15 | 2016-04-26 | 2016-08-22 | TANAP-WRP-TRA-VPF-0002 |  |  |  | 2016-12-01 | 2016-10-15 | 2016-10-01
[17 empty] | 70 |  | Actual Date: | 2015-09-14 | 2015-09-17 |  |  |  |  | Rev:RP3-C | RP3-C | 23 / 25 - %90
WRP-REQ-MEC-CS5-001 | ATLAS COPCO ENERGAS | ACE | GERMANY | Turbo Expander Generator TPI-22 |  |  |  | Note 1 | DOUGLAS LAWRIE HUSAMETTIN PEHLIVAN | N MEHDIYEV | ELNUR MAMMADOV | 1- PAUL NEUMANN 2- HERLEA LIVIU | ME | WRP-RFQ-PCP-GEN-047 | Action Tracker making good progress, next meeting to be held 29th March 2016, KOM took place 10th & 11th Feb 16, MOM issued 15th Feb 16, Some J-Type document overdue ! | B/2 | 70 | 2 | Planned Date: |  |  | 2016-01-19 | 29-Oct-15 | 2016-02-11 | TANAP-ACE-TRA-WRP-0001 | 2016-03-01 | 2016-03-01 | 2016-04-11 | 2016-05-31 | 2016-06-13 | TANAP-ACE-TRA-WRP-0002 |  |  |  | 2017-03-20 | 2017-03-20 | 2016-11-01
[19 empty] | Actual Date: | 2015-09-28 | 2015-10-06 |  | 2016-02-23 |  |  | Rev:RP3-C | Rev:RP3-D | 1 / 8 - %13
INSTRUMENTS
WRP-REQ-ICT-GEN-001 | HONEYWELL | HWL | BULGARIA | Integrated Control & Safety System TPI-23 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN | M KILINC / O OZCAN | PINAR COSKUN | 1- SEREF POLAT 2- REYHAN KURTULUŞ | IC | WRP–RFQ-PCP–GEN-012 | PO Awarded 25th Jan. Kick Off Meeting scheduled for 16th, 17th Feb. | C/3 |  | 0.5 | Planned Date: | 25-Mar-15 |  | 2016-01-25 | 24-Jun-15 | 2016-02-16 | TANAP-WRP-MOM-HWL-0001 | 2016-03-05 | 2016-03-05 | 2016-05-30 | 2016-06-16 | 2016-07-20 |  |  |  |  | 2017-01-31 | 2017-06-01 | 2017-01-01
[17 empty] | 75 |  | Actual Date: | 2015-08-05 | 2015-08-13 |  | 2016-02-16 |  |  | Rev:P3-1 | Rev:P3-0 | 0 / 10 - %0
WRP-REQ-ICT-GEN-010 | AKFEL | AKF | TURKEY | Metering Skids TPI-24 |  |  |  | Note 1 | EMRE EVGİ HUSAMETTIN PEHLIVAN | O OZCAN / M KILINC | PINAR COSKUN | 1-ONUR İĞRET 2-SUAT TUNC 3-SEREF POLAT 4-REYHAN KURTULUŞ | IC | WRP–RFQ-PCP–GEN-001 | PO Awarded 06-Nov. Kick off Meeting held 18th, 19th and 20-Nov. Revised Req issued 01st Dec. AKF-PCD-MTE-GEN-002 surface preparetion and painting procedure should be issued according with VDS. | B/2 |  | 1 | Planned Date: | 26-Jan-15 |  | 2015-11-06 | 2016-01-30 | 2015-11-18 | TANAP-WRP-MOM-AKF-0001 | 2016-02-29 | 2016-02-29 | 2016-02-08 | 2016-01-26 | 2016-04-26 | TANAP-WRP-MOM-AKF-0006 |  |  |  | 2016-10-15 | 2017-10-15 | 2016-10-01
[17 empty] | 75 |  | Actual Date: | 2015-04-29 | 2015-05-05 |  |  |  |  | Rev:P3-0 | Rev:P3-0 | 6 / 16 - %35
WRP-REQ-ICT-GEN-011 | MOKVELD | MKV | NEDERLAND | Control Valves SEVERE SERVICE TPI-25 |  |  |  | Note 1 | EMRE EVGİ HUSAMETTIN PEHLIVAN | M KILINC / O OZCAN | ALP NADI | TBA | IC | WRP–PLN-PCP-GEN-020 | Original TBE issued 06th Nov. Revised Severe service TBE issued 03rd Feb. Revised General Valves TBE issued 12th Feb. TANAP commercial to request Best and Final based on latest Bid Bulletin and Technical clarifications. | B/2 | 70 | 0.5 | Planned Date: | 18-Mar-15 |  | 2016-05-03 | 17-Jun-15 | 2016-06-07 | TANAP-WRP-MOM-MKV-0001 | 2016-07-04 | 2016-07-04 | 2016-08-22 | 2016-06-30 | [5 empty] | 2017-01-02 | 2017-04-01 | 2016-10-01
[19 empty] | Actual Date: | 2015-08-18 | 2015-08-25
WRP-REQ-ICT-GEN-011 | SEVERN GLOCON |  | UK / INDIA | Control Valves GENERAL SERVICE TPI- 40 |  |  |  | Note 1 | EMRE EVGİ HUSAMETTIN PEHLIVAN | M KILINC / O OZCAN | ALP NADI | TBA | IC | WRP–PLN-PCP-GEN-020 | Original TBE issued 06th Nov. Revised Severe service TBE issued 03rd Feb. Revised General Valves TBE issued 12th Feb. TANAP commercial to request Best and Final based on latest Bid Bulletin and Technical clarifications. | B/2 | 70 | 0.5 | Planned Date: | 18-Mar-15 |  | 2016-05-25 | 17-Jun-15 | 2016-06-27 |  | " | 2016-07-15 | 2016-07-30 | 2016-07-30 | [5 empty] | 2017-01-02 | 2017-04-01 | 2016-10-01
|  | SVG | [16 empty] | Actual Date: | 2015-08-18 | 2015-08-25
WRP-REQ-ICT-GEN-014 | GE |  | UK | Pressure Safety Relief Valves & Bursting Discs TPI-26 |  |  |  | Note 1 | KIVANÇ AĞİÇ | M KILINC / O OZCAN | ALP NADI | TBA | IC | WRP-RFQ-PCP-GEN-019 | Revised TBE issued 29th Jan. Revised data sheets issued as Bid Bulletin to 2 technically acceptable bidders 24th Feb with responses due back 01st Mar. | C/3 |  | 0.25 | Planned Date: | 18-Mar-15 |  | 2016-05-25 | 17-Jun-15 | 2016-06-25 |  | 2016-07-15 | 2016-07-15 | 2016-07-30 | 2016-07-30 | [5 empty] | 2017-01-02 | 2017-04-01 | 2016-10-01
[17 empty] | 50 |  | Actual Date: | 2015-10-07 | 2015-10-12
WRP-REQ-ICT-GEN-TBA | HONEYWELL | HWF | TURKEY | All Tagged Field Instruments (inc Transmitters (PL), Gauges(PL), Pressure Regulators(PL&ST), Flow Instruments(PL&ST) ) TPI-27 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN / TBA | O OZCAN / M KILINC | ELNUR MAMMADOV | TBA | IC | WRP-RFQ-PCP-GEN-046 | TBE issued formally via DCC. | D/4 |  | 0.25 | Planned Date: |  |  | 2016-05-15 | 17-Jun-15 | 2016-05-31 | TANAP-WRP-MOM-HWF-0001 | 2016-06-15 | 2016-06-15 | 2016-06-30 | 2016-06-30 | [5 empty] | 2016-07-29 | 2017-04-01 | 2016-03-01
[17 empty] | 70 |  | Actual Date: | 2015-11-26 | 2015-11-30
TELECOMMUNICATIONS
WRP-REQ-TEL-GEN-001 | CORNING | COC | TURKEY | Fibre Optical Cables For Onshore Pipeline and E90 Highway Routes TPI-30 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN / TBA | M KONYA / A CANSIZ | PINAR COSKUN | TBA | TC |  | RFQ package issued to Vendors 11th Feb, Bids due 10th March. First Delivery based on information received during Market Research from Vendors for total length of FOC. First Delivery date to be re-evaluated upon receipt of | D/4 |  | 0.5 | Planned Date: |  |  | 2016-05-15 |  | 2016-05-31 | TANAP-WRP-MOM-COC-0001 | 2016-06-26 | 2016-06-26 | 2016-07-14 | 2016-07-15 | [5 empty] | 2016-06-20 | 2016-06-20 | 2016-06-20
[17 empty] | 70 |  | Actual Date: | 2015-11-27 | 2015-11-27 |  | 2016-03-29
ELECTRICAL
WRP-REQ-ELE-CSG-001 | SCHNEIDER ELECTRIC | SND | TURKEY | HV/LT Transformers and Natural Earthing Resistors TPI-31 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN / TBA | U CAGLAR | ELNUR MAMMADOV | 1- REYHAN KURTULUŞ 2- SEREF POLAT | EL | WRP-RFQ-PCP-GEN-023 | PO Award Imminent; EPCM awaiting advanced copy of Contract to arrange Kick off Meeting as 16 th. March 2016. | B/2 |  | 0.5 | Planned Date: | 27-Apr-15 |  | 2016-03-08 | 27-Jul-15 | 2016-04-23 | TANAP-WRP-MOM-SND-0001 | 2016-05-30 | 2016-05-30 | 2016-05-19 | 2016-06-30 | [5 empty] | 2016-12-30 | 2017-06-01 | 2017-01-01
[17 empty] | 70 |  | Actual Date: | 2015-08-31 | 2015-09-01 |  | 2016-02-16
WRP-REQ-ELE-CSG-004 | EMERSON NETWORK POWER SYSTEMS | ENP | FRANCE - TURKEY | AC UPS + Battery + ACDB + DCDB TPI-33 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN / TBA | U CAGLAR | ELNUR MAMMADOV | TBA | EL | WRP-RFQ-PCP-GEN-025 | TBE issued 18th Jan. Best and Final Offers received in Ankara w/e 29th Jan. EPCM awaiting confirmation from Client of selected Vendor. | B/2 |  | 0.5 | Planned Date: | 27-Apr-15 |  | 2016-04-05 | 27-Jul-15 | 2016-04-20 | TANAP-WRP-MOM-ENP-0001 | 2016-05-07 | 2016-05-07 | 2016-06-25 | 2016-07-06 | [5 empty] | 2017-01-18 | 2017-06-01 | 2017-01-01
[17 empty] | 70 |  | Actual Date: | 2015-11-06 | 2015-11-10 |  | 2016-04-01
WRP-REQ-ELE-CSG-002 | ABB TURKEY | ABE | TURKEY | Switchgear Package (incl Distribution Boards/ Bus Duct + VSD/ Electrical Control System TPI-32 |  |  |  | Note 1 | HUSAMETTIN PEHLIVAN / TBA | U CAGLAR | ELNUR MAMMADOV | TBA | EL | WRP-RFQ-PCP-GEN-024 | Shortlist approved (4 bidders) 16th Dec .Bid Clarification completed, Draft TBE summary issued to Client 26th Feb. TBE forecast 04th March. | B/2 |  | 0.5 | Planned Date: |  |  | 2016-05-13 | 2016-03-26 | 2016-05-24 | TANAP-WRP-MOM-ABE-0001 | 2016-07-15 | 2016-07-15 | 2016-08-02 | 2016-08-10 | [5 empty] | 2016-11-22 | 2017-06-01 | 2017-01-01
[17 empty] | 70 |  | Actual Date: | 2015-12-14 | 2015-12-14 |  | 2016-04-13 |  |  |  |  | 0 / 17 - %0
PIPING
WRP-REQ-MTE-GEN-017 | VALVITALIA | VPC | ITALY | Station Manual Ball Valves (≥ NPS 24) & Actuated Ball Valves (all sizes) and Pipeline Actuated Ball & Plug Valves (≥ NPS 10) TPI-34 |  |  |  | Note 1 | EMRE EVGİ / AFSHIN MAAF | BONGERS /N MEHDIYEV | ALP NADI | 1-RAFAELE TOMBASCO 2-PAOLO BONO E | PI | WRP–RFQ-PCP–GEN-030 | Shortlisting approved (6 bidders). BCM’s completed; TBE formally issued Via DCC 26th Jan. EPCM awaiting confirmation from Client of selected Vendor | C/3 |  | 1 | Planned Date: | 14-May-15 |  | 2016-04-20 | 13-Aug-15 | 2016-05-10 | TANAP-WRP-MOM-VLC-0001 | 2016-06-17 | 2016-06-17 | 2016-06-18 | 2016-07-10 | 2016-07-15 |  |  |  |  | 2016-12-28 | 2017-05-01 | 2016-05-01
[17 empty] | 70 |  | Actual Date: | 2015-10-26 | 2015-10-28 |  | 2016-04-15 |  |  | Rev:P3-C | Rev:RP3-C | 2 / 14 - %15
WRP-REQ-MTE-GEN-022 | VALVITALIA | VCV | ITALY | Axial Check Valves (inc. Large Bore / Dual-plate) TPI-35 |  |  |  | Note 1 | EMRE EVGİ / AFSHIN MAAF | BONGERS /N MEHDIYEV | ALP NADI | 1-RICHARDO CHEROTTI 2- ALESSANDRO MATTARA | PI | WRP-RFQ-PCP-GEN-035 | PO Awarded 19th Jan. Kick off Meeting completed 3rd, 4th Feb. | C/3 |  | 0.5 | Planned Date: | 14-May-15 |  | 2016-01-20 | 2016-02-16 | 2016-02-04 | T ANAP-WRP-MOM-VCV-0001 | 2016-02-22 | 2016-03-14 | 2016-04-20 | 2016-05-03 | 2016-06-23 | T ANAP-WRP-MOM-VCV-0002 |  |  |  | 2016-09-30 | 2017-09-01 | 2016-09-01
[17 empty] | 70 |  | Actual Date: | 2015-09-15 | 2015-09-22 |  |  |  |  | Rev:P3-0 | Rev:P3-0 | 1 / 6 - %0
PIPELINES
WRP-REQ-PPL-PLG-001 | BAOSTEEL | BAO | CHINA | Main Pipeline Pipes & Induction Bends (LLI) - BAOSTEEL |  |  |  | Note 1 | LUIGI SALVATI | O BAYKAL / Z RAHMAN | A HASTURK | TUA | PL | ILF-RFQ-PCP-GEN-001 |  | B/2 |  | 2 | Planned Date: | 20-Mar-14 |  | 2014-10-14 | 2014-12-09 | 17-Nov-15 | TANAP-WRP-MOM-BAO-0001 | 2016-01-07 | 2015-09-16 | 17-Agu-15 | 2015-05-15 | 2014-11-15 | TANAP-WRP-MOM-BAO-0002 |  |  |  | 2015-04-24 | 2017-03-31 | 2015-05-29
[17 empty] | 70 |  | Actual Date: | 2014-07-21 | 2014-07-21 |  |  |  |  | RP3-0 | RP3-0 | 8 / 10 - %80
WRP-REQ-PPL-PLG-002 | TOSCELIK |  | TURKEY | Main Pipeline Pipes & Induction Bends (LLI) - TOSCELIK |  |  |  | Note 1 | LUIGI SALVATI | O BAYKAL / Z RAHMAN | A HASTURK | INTERTEK | PL | ILF-RFQ-PCP-GEN-001 |  | B/2 |  | 2 | Planned Date: | 20-Mar-14 |  | 2014-10-14 | 2014-12-09 | 04-Dec-14 |  | 2015-10-28 | 2015-10-28 | 23-Dec-14 | 2015-03-03 | 16-Dec-14 | TANAP-WRP-MOM-TOS-0001 |  |  |  | 2015-05-14 | 2017-04-30 | 2015-05-29
[17 empty] | 70 |  | Actual Date: | 2014-07-21 | 2014-07-21 |  |  |  |  | P3-0 | P3-0 | 9 / 10 - %90
WRP-REQ-PPL-PLG-003 | UMRAN |  | TURKEY | Main Pipeline Pipes & Induction Bends (LLI) - UMRAN EMEK |  |  |  | Note 1 | LUIGI SALVATI | O BAYKAL / Z RAHMAN | A HASTURK | INTERTEK | PL | ILF-RFQ-PCP-GEN-001 |  | B/2 |  | 2 | Planned Date: | 20-Mar-14 |  | 2014-10-14 | 2014-12-09 | 2015-12-03 |  | 2015-12-26 | 2015-12-26 | 23-Dec-14 | 2015-03-02 | 16-Dec-14 | TANAP-WRP-MOM-UEC-0002 |  |  |  | 2015-05-14 | 2017-04-30 | 2015-05-29
[17 empty] | 70 |  | Actual Date: | 2014-07-21 | 2014-10-14 |  |  |  |  | RP3-0 | RP3-0 | 9 / 10 - %90
WRP-REQ-PPL-PLG-004 | BNE | BNE | TURKEY | Main Pipeline Pipes & Induction Bends (LLI) - BNE |  |  |  | Note 1 | LUIGI SALVATI | O BAYKAL / Z RAHMAN | A HASTURK | INTERTEK | PL | ILF-RFQ-PCP-GEN-001 |  | B/2 |  | 2 | Planned Date: | 20-Mar-14 |  | 14-Oct-14 | 2014-12-09 | 2015-12-02 |  | 2015-12-24 | 39-Dec-15 | 2015-12-23 | 2015-02-25 | 16-Dec-14 | TANAP-WRP-MOM-BNE-0002 |  |  |  | 2015-05-14 | 2017-05-14 | 2015-05-29
[17 empty] | 40 |  | Actual Date: | 2014-07-21 | 2014-07-21 |  |  |  |  | RP3-0 | RP3-0 | 9 / 10 - %90
WRP-REQ-PPL-PLG-005 | VALVITALIA | VLV | ITALY | Main Pipeline Valves & Actuators (LLI) TPI-36 |  |  |  | Note 1 | EMRE EVGİ | O BAYKAL / Z RAHMAN | ALP NADI | 1-RAFAELE TOMBASCO 2-PAOLO BONO EMERSON: VICTOR REZA | PL | ILF-RFQ-PCP-GEN-002 |  | B/2 |  | 3 | Planned Date: | 18-Aug-14 |  | 2015-02-26 | 2015-04-23 | 2015-03-18 | TANAP-WRP-MOM-VLV-0001 | 08-Sep-15 | 2015-10-14 | 07-Sep-15 | 03-Jun-15 | 2015-09-11 | TANAP-WRP-MOM-VLV-0003 |  |  |  | 2015-10-31 | 2017-07-31 | 2015-12-01
[17 empty] | 70 |  | Actual Date: | 2014-08-18 | 2014-08-18 |  |  |  |  | RP3-0 | RP3-0 | 26 / 29 - %90
WRP-REQ-PPL-PLG-008 | PIPING TECHNOLOGIES | PTG | FRANCE | Pig Launchers & Receivers + Pig Signalling TPI-37 |  |  |  | Note 1 | KAAN DÖNMEZ / AFSHIN MAAF | O BAYKAL / Z RAHMAN | AHMET HASTURK | 1- ERIC GOMET 2- ? TEMP. PIG SIGNALLER-GERNARD OSTRAND | PL | WRP–RFQ-PCP–GEN-041 | Kick Off Meeting held for 25th and 26th Nov. Key Docs being received. Some J-Type document overdue! | C/3 |  | 0.5 | Planned Date: | 30-Mar-15 |  | 2015-11-10 | 2015-12-10 | 24-Nov-15 | TANAP-WRP-MOM-PTG-0001 | 2015-12-23 | 2016-01-22 | 2016-01-12 | 2016-04-12 | 2016-04-25 | TANAP-WRP-MOM-PTG-0002 |  |  |  | 2016-07-19 | 2017-02-14 | 2016-03-01
[17 empty] | 60 |  | Actual Date: | 2015-07-13 | 2015-07-13 |  |  |  |  | P3-0 | RP3-D | 13 / 20- %65
WRP-REQ-PPL-PLG-009 | EEW | EEW | GERMANY | Low Temperature Pipe and Induction Bends TPI-39 |  |  |  | Note 1 | KAAN DÖNMEZ LUIGI SALVATI | O BAYKAL / Z RAHMAN | A HASTUK | 1- ROBERT SCHOLL 2- YORK BRÜCKNER | PL | WRP-RFQ-PCP-GEN-050 |  | C/3 |  | 0.5 | Planned Date: |  |  | 2016-03-16 |  | 2016-03-23 | TANAP-WRP-MOM-EEW-0002 | 2016-04-18 | 2016-04-18 | 2016-04-18 | 2016-05-30 | 2016-06-20 | TANAP-WRP-MOM-EEW-0003 |  |  |  | 2016-07-12 | 2016-07-12 | 2016-05-01
[17 empty] | 50 |  | Actual Date: | 2016-01-06 | 2016-01-06 |  | 2016-05-04 |  |  | RP3-D | P3-D | 14 / 14- %100
WRP-REQ-PPL-GEN-001 | ALCADRAZ | ALC | NEDERLAND | Pig Trap Interlock System TPI-38 |  |  |  | Note 1 | DOUGLAS LAWRIE / AFSHIN MAAF | O BAYKAL / Z RAHMAN | PINAR COSKUN | TBA | PL | WRP-RFQ-PCP-GEN-049 |  | D/4 | 65 | 0.25 | Planned Date: | 26-Jun-15 |  | 2016-05-06 | 2016-03-26 | 2016-06-09 | TANAP-WRP-MOM-ALZ-0001 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-07-20 | [5 empty] | 2016-09-23 | 2016-09-23 | 2016-03-01
[19 empty] | Actual Date: |  |  |  | 2016-04-13